## Sheet1
Deliverables
Lab 1
Team Registration | 10 | Complete
Meeting minutes (Lab) | 10 | Complete
Wiki: Team Information | 10 | Complete
Wiki: Project Proposal | 10 | Complete
Wiki: Use Case Model | 10 | Incomplete
Wiki: Backlog | 10 | Complete
Wiki: Meeting minutes | 10 | Complete
Lab 2
Meeting minutes (Lab) | 8 | Incomplete
Wiki: System Requirement Specification | 8 | Incomplete
Wiki: Quality Plan | 8 | Incomplete
Wiki: Backlog | 8 | Incomplete
Wiki: Meeting minutes | 8 | Incomplete
Lab 3
Meeting minutes (Lab) | 6 | Incomplete
Wiki: Project Plan | 6 | Incomplete
Wiki: Risk Management | 6 | Incomplete
Demo: Prototype | 6 | Incomplete
SVN: Prototype Code | 6 | Incomplete
SVN: Prototype Documents | 6 | Incomplete
SVN: Prototype Video Clips | 6 | Incomplete
SVN: Prototype Slides | 6 | Incomplete
Wiki: Backlog | 6 | Incomplete
Wiki: Meeting minutes | 6 | Incomplete
Lab 4
Meeting minutes (Lab) | 4 | Incomplete
Prototype Demonstartion | 4 | Incomplete
Wiki: Design Report on Software Maintainability | 4 | Incomplete
Wiki: Configuration Management Plan | 4 | Incomplete
Wiki: Change Management Plan | 4 | Incomplete
Wiki: Release Plan | 4 | Incomplete
Wiki: Backlog | 4 | Incomplete
Wiki: Meeting minutes | 4 | Incomplete
Lab 5
Presentation | 2 | Incomplete
Meeting minutes (Lab) | 2 | Incomplete
Wiki: Presentation Slides | 2 | Incomplete
Wiki: Test Plan | 2 | Incomplete
Wiki: Test Cases and Requirements Test Coverage Report | 2 | Incomplete
Wiki: CMMI Level 2 Definition | 2 | Incomplete
SVN (Version Control System): All documents checked in | 2 | Incomplete
Wiki: Backlog | 2 | Incomplete
Wiki: Meeting minutes | 2 | Incomplete
NTULearn: Peer Review | 2 | Incomplete
Programming
Name | Priority (1-10) | Status
Player
Player Direction Movement | 10 | Complete | Poshi
Player Jumping Movement | 10 | Complete | Poshi
Player Death | 10 | Incomplete | Poshi
Player Health | 10 | Incomplete | Poshi
Player Shooting Action | 9 | Incomplete | Poshi
Player Skill (Basket Ball) | 8 | Incomplete
Player Skill (Badminton) | 8 | Incomplete
Player Ultimate skill (Basket Ball) | 8 | Incomplete
Player Ultimate Skill (Badminton) | 8 | Incomplete
Environment
Endless Platform Generation | 10 | Complete | Poshi
Generic Object Pooling | 10 | Complete | Poshi
Coin Spawning | 8 | Complete | Fabian
Obstacle Spawning (Static) | 7 | Complete | Fabian
Obstacle Logic (Static) | 7 | Complete | Fabian
Obstacle Spawning (Moving) | 7 | Complete | Fabian
Obstacle Logic (Moving) | 7 | Complete | Fabian
Enemies
Enemy Spawning | 8 | Incomplete | Shengzhe
Enemy Damage (Hoop Zombie) | 8 | Incomplete | Shengzhe
Enemy Movement (Hoop Zombie) | 8 | Incomplete | Shengzhe
Enemy Damage (Badminton Zombie) | 8 | Incomplete | Shengzhe
Enemy Health | 8 | Incomplete | Shengzhe
Enemy Death | 8 | Incomplete | Shengzhe
Boss Enemy Spawning | 5 | Incomplete
Boss Enemy Movement (Basketball) | 5 | Incomplete
Boss Enemy Movement (Badminton) | 5 | Incomplete
Boss Enemy Attack (Basketball) | 5 | Incomplete
Boss Enemy Attack (Badminton) | 5 | Incomplete
Boss Enemy Health | 5 | Incomplete
Boss Enemy Death | 5 | Incomplete
UI
Start Button Logic | 6 | Incomplete | Ryan
Exit Button Logic | 6 | Incomplete | Ryan
Credit Button Logic | 6 | Incomplete | Ryan
Pause Button Logic | 6 | Incomplete | Ryan
Power-ups
Coin Magnet Mechanics | 4 | Complete | Fabian
Invincibility Mechanics | 4 | Complete | Fabian
Enchancement
Immortality Mechanics | 3 | Incomplete | Fabian
Coin Master | 3 | Incomplete | Fabian
Arcade Expert | 3 | Incomplete | Fabian
Art
Name | Priority (1-10) | Status
Character
Character Sprite | 7 | Incomplete | Zixing
Basketball Sprite | 7 | Incomplete | Zixing
Badminton Sprite | 7 | Incomplete | Zixing
Enemies
Zombie Sprite(Hoop) | 6 | Incomplete
Zombie Sprite(Racket) | 6 | Incomplete
Boss Enemy Sprite(Basketball) | 4 | Incomplete
Boss Enemy Sprite(Badminton) | 4 | Incomplete
Environment
Background Scrolling Image | 7 | Incomplete | Hermes/Zihoe
Structure Sprites | 7 | Incomplete | NA
Platform Sprites | 7 | Incomplete | Hermes
Obstacle Sprite(Basketball Rim) | 6 | Incomplete | Hermes
Obstacle Sprite(Badminton Net) | 6 | Incomplete | Zihoe
Obstacle Sprite(Basketball) | 6 | Incomplete | Hermes
Obstacle Sprite(Badminton) | 6 | Incomplete | Zihoe
UI
Start Button Image | 5 | Incomplete | Ryan
Exit Button Image | 5 | Incomplete | Ryan
Pause Button Image | 5 | Incomplete | Ryan
Credit Button Image | 5 | Incomplete | Ryan
Movement Visual (Joystick) | 5 | Incomplete | NA
Life Visual | 5 | Incomplete | NA
Ultimate skill charge bar | 5 | Incomplete | NA
Skill button Image | 5 | Incomplete | NA
Shop Button Image | 3 | Incomplete | Ryan
Power-Ups
Power up Icon (Coin Magnet) | 3 | Incomplete
Power up Icon (Invincibility) | 3 | Incomplete
Enchancement
Enchancement Icon (Immortality) | 2 | Incomplete
Enchancement Icon (Coin Master) | 2 | Incomplete
Enchancement Icon (Arcade expert) | 2 | Incomplete
Animations
Character
Character Idle Animation | 5 | Incomplete
Character Movement Animation | 5 | Incomplete
Character Death animation | 5 | Incomplete
Character Attacking Animation (Basketball) | 5 | Incomplete
Character Attacking Animation (Badminton) | 5 | Incomplete
Character Skill Animation (Basketball) | 4 | Incomplete
Character Skill Animation (Badminton) | 4 | Incomplete
Character Ultimate animation (Basketball) | 4 | Incomplete
Character Ultimate animation (Badminton) | 4 | Incomplete
Enemies
Enemy Movement Animation (Zombie Hoop) | 4 | Incomplete
Enemy Idle Animation (Zombie Racket) | 4 | Incomplete
Enemy Death Animation (Zombie Hoop) | 4 | Incomplete
Enemy Death Animation (Zombie Racket) | 4 | Incomplete
Boss Movement Animation (Basketball) | 3 | Incomplete
Boss Movement Animation (Badminton) | 3 | Incomplete
Boss Attack Animation (Basketball) | 3 | Incomplete
Boss Attack Animation (Badminton) | 3 | Incomplete
Sound
Level
Background music | 5 | Incomplete
Character
Character Hit sound | 3 | Incomplete
Character Attack sound | 3 | Incomplete
Character Jumping sound | 3 | Incomplete
Character Death sound | 3 | Incomplete
Character Skill sound | 3 | Incomplete
Character Ultimate sound | 3 | Incomplete
Enemies
Enemy Spawning | 2 | Incomplete
Enemy Hit Sound | 2 | Incomplete
Enemy Death Sound | 2 | Incomplete
Enemy attack Sound (Zombie Hoop) | 2 | Incomplete
Enemy Attack Sound (Zombie Racket) | 2 | Incomplete
Boss Enemy Spawning Sound (Basketball) | 1 | Incomplete
Boss Enemy Spawning Sound (Badminton) | 1 | Incomplete
Boss Enemy Attacking Sound (Basketball) | 1 | Incomplete
Boss Enemy Attacking Sound (Badminton) | 1 | Incomplete
Boss Enemy Death Sound (Basketball) | 1 | Incomplete
Boss Enemy Death Sound (Badminton) | 1 | Incomplete
Power-ups
Coin Magnet Power-up Sound | 1 | Incomplete
Invincibility Power-up Sound | 1 | Incomplete
FX
Character
Player Skill Effect (Basketball) | 2 | Incomplete
Player Skill Effect (Badminton) | 2 | Incomplete
Player Ultimate Skill Effect (Basketball) | 2 | Incomplete
Player Ultimate Skill Effect (Badminton) | 2 | Incomplete
Enemies
Boss Attacking Effect (Basketball) | 1 | Incomplete
Boss Attacking Effect (Badminton) | 1 | Incomplete
Power-ups
Coin Magnet Effect | 1 | Incomplete
Invincibility Effect | 1 | Incomplete
State Transition Diagram