## Sheet1
| Risk | Risk Description | Impact Severity | Probability | Impacts | Risk Reduction
1 | Scope and requirements | Unclear requirements | High | 20% | Depending on the stage at which the changes occur, could range from needing to update the requirements documentation to needing to do a complete redesign. | Be rigorous in eliciting requirements. Make customers aware of potential repercussions of requirement changes.
2 | Scope and requirements | Feasibility of requirements | High | 25% | Requirements that are not feasible are unable to be produced by the development team. Customers might receive a nasty shock once the end product is produced and requirements are no fulfiled. | Be sure to go through each of the requirement and bring up potential issues such as feasibility wise to the customer. Alternatives can be suggested to the customers.
3 | HR management | Project Management Restructure | Low | 5% | May cause delay in project schedule and affect deadlines that have to be met | Ensure that all relevant parties are well suited and satisfied with the initial structure of the project management
4 | Communications and decision making | Incompetence in decision making | Moderate | 10% | Can create potential situations where there is conflict among team members or lead may lead to poor execution of the project timeline | Appoint a suitable canidate to lead the project and make sure there are several points of contact in case the canidate fall short
5 | Enterprise environment factor | Lack of expertise | Moderate | 30% | There would be more work for remaining employees, and any specialized skills or knowledge would be lost. | Offer benefits and incentives to staff.
6 | Lack of Risk Management | Underestimation of Project Size | High | 25% | More work will need to be spent on design and coding; could negatively impact | Update estimates often as the project progresses.
7 | Lack of Risk Management | Secondary Risk | Low | 5% | Arises as an outcome of implementing a risk response and often these risks are deemed as the better choice take in the long run | A response plan can be created to reduce the impacts of such risks
8 | Lack of Risk Management | Residual Risk | Low | 30% | Residual risks are usually manageable and are acceptable to the organisation's risk tolerance level | Accept the risks that are remaining
9 | Technical solutions | High rate of bugs & other software related issue | High | 30% | May cause program to crash | Thoroughly read through and understand every piece of re-used code before implementing to source code
10 | Technical solutions | Inefficient code | Low | 35% | Makes it hard for the adding of new features in the future. Might increase the cost of developing an inefficiient software | In the event of encountering such codes, fixing the code should be a priority. Programmers and testers should acquire a high level of self-discipline in the way the code is designed, written and tested.
11 | Technical solutions | Integration | Moderate | 20% | May cause program to crash | Keep software simple and development team should always know the progress of each member.
12 | External risks | User acceptance | High | 1% | All work will have been wasted. | Keep in close contact with customers. Ensure that they have some market research indicating a demand for this product
13 | External risks | Changes in covid-19 Measures | Moderate | 30% | Certain rules and regulations might have to be changed in a notice time. Certain features in the product might have to be changed too . | Have a response plan in the event that this happens. Have a buffer time in the project timeline so that such distruptions can be accounted for.